## 📋 WBS Master
UNICIRCUIT ENGINEERING SERVICES ¦ SALES TEAM WORK BREAKDOWN STRUCTURE ¦ 3-MONTH EXECUTION PLAN
Owner: NSM + BDMs + Founders ¦ Territories: Raipur (CG) + Nagpur (MH) ¦ Tool Stack: M365 + WhatsApp + LLM Platform ¦ Target: ₹18 Cr Pipeline in 90 Days
WBS TREE — 6 WORK PACKAGES → 24 DELIVERABLES → 120+ TASKS
WP # | Work Package | Deliverables (5 per WP) |  |  |  | Owner | Target Month
WP-1 | TEAM & TERRITORY SETUP | 1.1 Org chart finalized + roles defined |  |  |  | NSM | Month 1
1.2 Territory assignments mapped (Raipur / Nagpur / National)
1.3 50 dream accounts assigned to BDMs
1.4 KPIs & incentives communicated to team
1.5 Tool access granted (M365, HubSpot, WA, LLM Dashboard)
WP-2 | LEAD GENERATION & PROSPECTING | 2.1 50 Tier-1 account contacts identified (Apollo.io) |  |  |  | BDMs + NSM | Month 1–2
2.2 Email outreach sequences launched (Outlook)
2.3 WhatsApp broadcast lists built & first msg sent
2.4 LinkedIn social selling activated
2.5 Partner referral pipeline opened
WP-3 | ENGAGEMENT & QUALIFICATION | 3.1 Discovery calls conducted (PBX logged) |  |  |  | BDMs | Month 1–3
3.2 BANT qualification completed per account
3.3 Demo / presentation delivered (MS Teams)
3.4 Site visits conducted (field BDMs)
3.5 Needs assessment forms submitted (MS Forms)
WP-4 | PROPOSAL & NEGOTIATION | 4.1 Proposals generated & submitted |  |  |  | NSM + Pre-Sales | Month 2–3
4.2 Technical presentations prepared
4.3 Commercial terms negotiated
4.4 Reference site visits arranged for prospects
4.5 Legal / compliance docs prepared
WP-5 | GOVT/PSU & TENDER | 5.1 GeM registration completed |  |  |  | Govt Lead + NSM | Month 1–3
5.2 Tender tracking sheet maintained weekly
5.3 Tender bids submitted on time
5.4 Empanelment applications submitted
5.5 Vendor meets / GeM buyer connect attended
WP-6 | PIPELINE MANAGEMENT & REPORTING | 6.1 CRM updated daily (HubSpot / Zoho) |  |  |  | NSM + Founders | Monthly
6.2 Weekly pipeline review conducted (Teams)
6.3 Monthly sales report submitted
6.4 Win/loss debrief documented
6.5 Q2 forecast prepared at Month 3 end
3-MONTH TARGET SUMMARY
Work Packages |  | Total Deliverables | Dream Accounts | Pipeline Target | Demos Target | Deals to Close
6 |  | 30 | 50 | ₹18 Cr | 30+ | ₹3 Cr

## 📅 Daily-Weekly Standards
SALES TEAM ¦ DAILY & WEEKLY ACTIVITY STANDARDS — MINIMUM PERFORMANCE BENCHMARKS
DAILY MINIMUM ACTIVITY STANDARDS (Per Role)
Role | Cold Calls (PBX) | Follow-up Calls | Emails Sent | WhatsApp Messages | CRM Updates | LinkedIn Actions | New Contacts | Notes Logged | Meetings Booked
NSM (National Sales Mgr) | 5 | 10 | 15 | 10 | All team | 3 | 2 | All | 1 demo/day
BDM – Raipur | 8 | 12 | 10 | 15 | 5 | 3 | 3 | 5 | 1 meeting/day
BDM – Nagpur | 8 | 12 | 10 | 15 | 5 | 3 | 3 | 5 | 1 meeting/day
Pre-Sales / Technical | 2 | 5 | 10 | 5 | 3 | 2 | 1 | 3 | 1 proposal/2 days
Govt Sales Specialist | 5 | 8 | 12 | 8 | 4 | 2 | 2 | 4 | 1 tender review/day
Founder (Active Sales) | 3 | 5 | 10 | 5 | 2 | 2 | 1 | 2 | 2 C-level meetings/week
WEEKLY SALES CADENCE (Non-Negotiable Rhythm)
Day / Time | Activity | Who | Duration | Tool Used | Output Required | CRM Action
MONDAY 9:00 AM | Weekly Pipeline Review (Teams call) | NSM + All BDMs + Founders | 45 min | MS Teams + HubSpot | Updated pipeline slide Deal status per BDM 3 priority accounts for week | All deals updated before meeting
MONDAY 10:00 AM | AI Digest Review (from LLM Platform) | NSM + Founders | 20 min | UniIntelligence Dashboard | Hot leads actioned Tender alerts reviewed Top 3 follow-ups assigned | New tasks created in Planner
TUESDAY–THURSDAY | Field / Call Activity Block | BDMs (Raipur + Nagpur) | Full Day | PBX + WhatsApp + Outlook | Min 8 calls/day logged All WA responded within 2 hrs Visit notes entered same day | Call logged in CRM within 1 hr
WEDNESDAY 5:00 PM | Deal Health Check (NSM + BDMs) | NSM + BDMs | 30 min | HubSpot + MS Teams | Stuck deals identified Escalation to founder if needed Proposal status updated | Stage changes logged
FRIDAY 4:00 PM | Weekly Activity Self-Report | All BDMs → NSM | 20 min | MS Forms / Email | Calls made, emails sent, WA msgs Pipeline ₹ moved Blockers flagged | NSM compiles team summary
FRIDAY 5:00 PM | Next Week Planning | NSM + BDMs | 30 min | MS Planner + HubSpot | Top 10 follow-ups scheduled New demos booked Proposals due next week | Follow-up tasks created in Planner
MONTHLY (1st Monday) | Monthly Business Review (MBR) | Founders + NSM + Full Team | 90 min | Power BI + MS Teams | vs target dashboard Win/loss review Q-month plan for next 30 days | Full pipeline snapshot exported
RESPONSE TIME STANDARDS (All Team Members)
Channel | Inbound Lead Type | Response Time Target | First Response Template | Escalate to NSM if | Log Where
📧 Email | Cold inbound enquiry | Within 4 business hours | Acknowledge + ask for 15-min call / share brochure link | Budget > ₹50L or C-level sender | HubSpot email + Outlook
📧 Email | Tender / RFQ / NIT | Within 2 hours | Acknowledge receipt + confirm evaluation timeline | Always — loop NSM + Founder immediately | Tender tracker + HubSpot
💬 WhatsApp | Product enquiry | Within 1 hour | Hi [Name], thanks for reaching out to Unicircuit! I'll call you in 30 mins. | No response in 1 hr — auto-alert to NSM | WA Business + HubSpot note
💬 WhatsApp | Existing prospect follow-up | Within 30 minutes | Direct, contextual reply referencing last discussion | Prospect mentions competitor or price pressure | HubSpot interaction log
📞 Missed Call (PBX) | Any inbound call | Call back within 1 hour | Call + follow WA: 'Missed your call – calling back shortly' | 3+ missed calls from same number — Hot lead flag | PBX CDR + HubSpot
🔔 Tender Portal Alert | GeM / CPP / NIT notification | Review within same day | NSM + Govt Lead evaluate bid-no-bid within 24 hrs | Always escalate to Founders for bids > ₹1 Cr | Tender tracker + Planner

## 📍 BDM Raipur Tasks
BDM TASK TRACKER — TERRITORY: RAIPUR, CHHATTISGARH ¦ Unicircuit Engineering Services
Target Sectors: Govt/PSU (CSIDC, CSPDCL, BHILAI STEEL, SAIL) ¦ Industrial (Raipur SIDCUL, NSEZ) ¦ Smart City (Raipur Smart City Dev Corp) ¦ Education (NIT Raipur, AIIMS Raipur)
Mo | Wk | Task Name | Sub-Tasks / Actions | Tool | Owner | Deliverable / Done Criteria | Status | Pipeline ₹ | Segment
M1 | W1 | Account Mapping | Map 25 Raipur-specific target accounts in HubSpot Verify contact names via LinkedIn + Apollo.io Assign tier (1/2/3) to each account | HubSpot + Apollo.io | NSM | 25 accounts in HubSpot with tier tag | ⬜ TODO | ₹ – | Govt/PSU, Industrial
M1 | W1 | WhatsApp Setup | Create 3 WA broadcast lists for Raipur: • Govt/PSU contacts • Industrial accounts • Smart City / Education | WhatsApp Business | BDM Raipur | 3 broadcast lists ready, 20+ contacts each | ⬜ TODO | ₹ – | All
M1 | W2 | Cold Outreach Email | Send first cold email to 25 Raipur accounts Use Outlook sequence (5-email series) Attach company profile + brochure PDF (SharePoint link) | Outlook + SharePoint | BDM Raipur | 25 emails sent, opens tracked in HubSpot | ⬜ TODO | ₹ – | All
M1 | W2 | WA Intro Broadcast | Send intro WA broadcast to all Raipur lists Include: company name, 2-line capability, deck link Follow up on replies within 1 hour | WhatsApp Business | BDM Raipur | Broadcast sent, replies logged in CRM | ⬜ TODO | ₹ – | All
M1 | W3 | Discovery Calls | Make min 40 outbound calls (8/day × 5 days) Target: CSIDC, CSPDCL, SAIL, NIT Raipur, AIIMS Raipur Log ALL calls in PBX CDR → auto-synced to LLM platform | PBX + HubSpot | BDM Raipur | 40 calls made, 5+ demos booked | ⬜ TODO | ₹ – | Govt/PSU, Education
M1 | W3 | Meeting Booking | Book 5 physical meetings in Raipur Priority: CSIDC CMD / CSPDCL GM / BHILAI STEEL Confirm via WA 24 hrs before meeting | Outlook + WA | BDM Raipur | 5 meetings confirmed & in Outlook calendar | ⬜ TODO | ₹ – | Govt/PSU
M1 | W4 | Demos (MS Teams) | Conduct 3 product demos via MS Teams Solutions: Smart Surveillance + Smart Building Send post-demo feedback form (MS Forms) | MS Teams + MS Forms | BDM Raipur + Pre-Sales | 3 demos done, feedback forms returned | ⬜ TODO | ₹ – | Raipur prospects
M1 | W4 | Partner Identification | Identify 3 Raipur-based system integrators / consultants Initiate partner discussion via email + WA Share partner program info | Outlook + WA | BDM Raipur | 3 partners in discussion | ⬜ TODO | ₹ – | Partners
M2 | W5 | Proposal Submission | Submit 3 proposals for Raipur top accounts Use LLM-generated first draft + BDM edits Deliver via email + WA confirmation | Word (M365) + LLM Platform | BDM Raipur + Pre-Sales | 3 proposals submitted & acknowledged | ⬜ TODO | ₹3 Cr | All
M2 | W5 | Govt/PSU Deep Dive | Schedule meetings with 5 Govt accounts: CSIDC, CSPDCL, SAIL Bhilai, CPWD Raipur, NIT Raipur Carry printed collateral + company profile | Outlook + PBX | BDM Raipur | 5 Govt meetings completed | ⬜ TODO | ₹5 Cr | Govt/PSU
M2 | W6 | GeM Buyer Connect | Identify GeM-registered buyers in Raipur Register & link Unicircuit GeM catalog Share GeM product listings via email to relevant contacts | GeM Portal + Outlook | Govt Lead + BDM | GeM buyers mapped, listings live | ⬜ TODO | ₹ – | Govt/PSU
M2 | W6 | Tender Tracking | Monitor: CPWD NIT, CSIDC tenders, NIT Raipur e-tenders Weekly scan on CPP Procurement + GeM portal Bid-no-bid decision within 24 hrs of finding | CPP Portal + GeM + Planner | BDM Raipur + NSM | Weekly tender log updated | ⬜ TODO | ₹2 Cr | Govt/PSU
M2 | W7 | Proposal Follow-up | Follow up on all 3 submitted proposals WA message + call 5 days after submission Address objections — loop in NSM/Technical if needed | WA + PBX | BDM Raipur | Follow-ups done, next step confirmed | ⬜ TODO | ₹3 Cr | All
M2 | W8 | Site Visit Coordination | Arrange 1 reference site visit for shortlisted Raipur prospect Coordinate with existing Unicircuit client site Prepare visit agenda | Outlook + WA | BDM Raipur + Pre-Sales | 1 site visit completed | ⬜ TODO | ₹1 Cr | Top prospect
M3 | W9 | Negotiation Support | Support negotiation for 3 active deals Prepare commercial comparison sheet Loop founder for final pricing approval | Excel + WA + Outlook | BDM Raipur + Founder | Deal terms agreed, LOI/PO expected | ⬜ TODO | ₹3 Cr | Hot deals
M3 | W10 | Close First Deal | Target: Close 1 deal by end of Month 3 Priority: CSIDC or BHILAI STEEL account PO / Work Order received + CRM marked Won | Outlook + HubSpot | BDM Raipur + NSM | ₹1 Cr+ deal closed, PO received | ⬜ TODO | ₹1 Cr | Tier-1
M3 | W11 | Partner MoU Sign | Sign MoU with 2 Raipur partners Conduct partner product training (MS Teams) Set up deal registration process | SharePoint + WA + Teams | BDM Raipur | 2 MoUs signed, partners active | ⬜ TODO | ₹ – | Partners
M3 | W12 | Territory Report | Submit Raipur territory Month 3 report: Pipeline value, accounts engaged, deals won/lost Q2 target accounts identified | Power BI + Excel | BDM Raipur → NSM | Territory report submitted by Month-3 end | ⬜ TODO | ₹ – | All

## 📍 BDM Nagpur Tasks
BDM TASK TRACKER — TERRITORY: NAGPUR / VIDARBHA, MAHARASHTRA ¦ Unicircuit Engineering Services
Target Sectors: Industrial (WCL, NTPC Koradi/Khaperkheda, MSEDCL) ¦ Smart City (Nagpur Smart City Dev Corp, MIHAN SEZ) ¦ Education (VNIT, AIIMS Nagpur) ¦ Commercial (Nagpur Metro, Butibori MIDC)
Mo | Wk | Task Name | Sub-Tasks / Actions | Tool | Owner | Deliverable / Done Criteria | Status | Pipeline ₹ | Segment
M1 | W1 | Account Mapping | Map 25 Nagpur/Vidarbha target accounts in HubSpot Key: NTPC Koradi, NTPC Khaperkheda, WCL, MSEDCL, MIHAN SEZ Verify DGM/GM-level contacts via LinkedIn | HubSpot + Apollo.io | NSM | 25 accounts in HubSpot with tier tags | ⬜ TODO | ₹ – | Industrial, Govt/PSU
M1 | W1 | WA Broadcast Lists | Create Nagpur broadcast lists: • Power sector (NTPC, MSEDCL, WCL) • Smart City / SEZ (MIHAN, Nagpur Smart City) • Education + Health (VNIT, AIIMS Nagpur) | WhatsApp Business | BDM Nagpur | 3 broadcast lists built, msgs drafted | ⬜ TODO | ₹ – | All
M1 | W2 | Email Campaign Launch | Send cold email campaign to 25 Nagpur accounts Subject lines tailored per sector Attach: Smart Building + Industrial Asset Mgmt brochure | Outlook + HubSpot | BDM Nagpur | 25 emails sent, open rate tracked | ⬜ TODO | ₹ – | All
M1 | W2 | NTPC Priority Outreach | Priority approach for NTPC Koradi + NTPC Khaperkheda: Call General Manager (O&M / Electrical) WA intro with Unicircuit credentials + relevant case study | PBX + WA | BDM Nagpur | NTPC contact established, meeting requested | ⬜ TODO | ₹3 Cr | Govt/PSU
M1 | W3 | Industrial Site Visits | Visit MIDC Butibori + MIHAN SEZ — meet facilities managers Carry physical demo kit (tablet + presentation) Post-visit: WA follow-up within 24 hrs | Field + WA + Outlook | BDM Nagpur | 2 MIDC/MIHAN site visits completed | ⬜ TODO | ₹ – | Industrial
M1 | W3 | VNIT / AIIMS Engagement | Contact admin/purchase department: VNIT Nagpur – Registrar / Purchase Officer AIIMS Nagpur – CMO / Hospital Superintendent Share smart campus / hospital security solution brief | Email + PBX + WA | BDM Nagpur | Education/Health contacts established | ⬜ TODO | ₹1 Cr | Education/Health
M1 | W4 | Discovery Call Blitz | 40 discovery calls in Nagpur region (8/day × 5 days) Focus: MSEDCL sub-divisions, WCL area offices All logged via PBX → LLM auto-summary | PBX | BDM Nagpur | 40 calls logged, 5 demos booked | ⬜ TODO | ₹ – | Power sector
M1 | W4 | Nagpur Smart City Connect | Contact Nagpur Smart City Development Corporation Meet Project Manager / DGM-IT Present: Smart Surveillance + Smart Building capabilities | Email + WA + MS Teams | BDM Nagpur | Smart City meeting booked | ⬜ TODO | ₹2 Cr | Smart City
M2 | W5 | NTPC Proposal | Prepare tailored proposal for NTPC Koradi: Scope: Industrial Asset Management + Surveillance Technical presentation by Pre-Sales team (Teams call) Submit within 2 weeks of demo | Word + LLM Platform + Teams | BDM Nagpur + Pre-Sales | NTPC proposal submitted | ⬜ TODO | ₹4 Cr | Govt/PSU
M2 | W5 | WCL Proposal | Prepare proposal for Western Coalfields Limited: Scope: Physical Security + ELV + Digital Infrastructure Coordinate with HQ for WCL-specific compliance docs | Word + LLM + Outlook | BDM Nagpur + NSM | WCL proposal submitted | ⬜ TODO | ₹3 Cr | Govt/PSU
M2 | W6 | MIHAN SEZ Engagement | Meet MIHAN SEZ Developer (MAHAGENCO / MIAL) Scope: Smart Building + Connectivity for SEZ campus Present connected campus reference project | Field + MS Teams | BDM Nagpur | MIHAN SEZ meeting + proposal request | ⬜ TODO | ₹2 Cr | Industrial/SEZ
M2 | W6 | Nagpur Metro Outreach | Contact Nagpur Metro Rail Corporation: Dept: Rolling Stock / Infrastructure / IT Scope: Physical Security, ELV, CCTV systems | Email + WA + PBX | BDM Nagpur | Nagpur Metro contact established | ⬜ TODO | ₹1.5 Cr | Govt/PSU
M2 | W7 | Demo Delivery | Conduct 5 demos for Nagpur pipeline: Mix of on-site demos + MS Teams virtual Pre-Sales lead for technical Q&A | MS Teams + Field | Pre-Sales + BDM | 5 demos completed, feedback collected | ⬜ TODO | ₹8 Cr | All
M2 | W8 | Partner Network – Nagpur | Identify 3 Nagpur-based EPC / system integrators Conduct partner intro (Teams + in-person) Sign LOI / MoU with 2 partners | Outlook + WA + SharePoint | BDM Nagpur | 2 Nagpur partner MoUs signed | ⬜ TODO | ₹ – | Partners
M3 | W9 | NTPC / WCL Follow-up | Intensive follow-up on NTPC + WCL proposals Address commercial objections — Founder loop-in Request PO / work order timeline from procurement | WA + PBX + Outlook | BDM Nagpur + Founder | PO timeline confirmed from NTPC/WCL | ⬜ TODO | ₹7 Cr | Govt/PSU
M3 | W10 | Tender Response – Nagpur | Active bids: MSEDCL open tender / Nagpur Smart City RFP Coordinate tender doc preparation with Pre-Sales Submit before deadline | CPP Portal + SharePoint | BDM Nagpur + Govt Lead | 1-2 tenders submitted | ⬜ TODO | ₹3 Cr | Govt/PSU
M3 | W11 | Reference Site Visit | Arrange client reference site for NTPC/WCL decision-makers Coordinate with existing Unicircuit client (power sector) Prepare visit pack + agenda | Outlook + WA | BDM Nagpur + Pre-Sales | Reference visit completed | ⬜ TODO | ₹5 Cr | Hot prospects
M3 | W12 | Territory Q2 Plan | Submit Nagpur territory Month 3 report: Pipeline: Engaged accounts, deal stages, ₹ value Q2 account list: 10 new + 15 carry-over | Power BI + Excel | BDM Nagpur → NSM | Territory report + Q2 plan submitted | ⬜ TODO | ₹ – | All

## 🎯 NSM Tasks
NSM TASK TRACKER — NATIONAL SALES MANAGER ¦ Unicircuit Engineering Services
Scope: All Territories ¦ Manages: BDM Raipur + BDM Nagpur + Pre-Sales + Govt Lead ¦ Reports to: Founders ¦ Key Focus: Team Productivity + Pipeline Quality + Deal Closure
Mo | Wk | Task Name | Sub-Tasks / Actions | Tool | Owner | Done Criteria | Status | Priority
M1 | W1 | Team Onboarding | Onboard BDM Raipur + BDM Nagpur: • Issue M365 accounts + HubSpot access • Walkthrough of CRM pipeline stages • Territory account list handover • Set 90-day individual targets (KPIs sheet) | M365 + HubSpot | NSM | Both BDMs operational Day 1 | ⬜ TODO | HIGH
M1 | W1 | Sales Playbook Creation | Create Unicircuit Sales Playbook document: • 5-stage sales process • Objection handling per segment • Email / WA message templates • Product-to-sector fit matrix | Word (M365) + SharePoint | NSM + Founders | Playbook published on SharePoint | ⬜ TODO | HIGH
M1 | W1 | CRM Architecture Setup | Set up HubSpot pipeline stages: Target → Contacted → Demo → Proposal → Negotiation → Won/Lost Custom properties: Territory, Sector, Service Line, BANT Score Import 50 dream accounts | HubSpot | NSM | CRM live with 50 accounts, stages set | ⬜ TODO | HIGH
M1 | W2 | LLM Platform Briefing | Brief backend developer: • Share 50 account list • Define BANT scoring criteria • Approve prompt templates (call, email, WA) • Define CRM sync fields | Teams + Docs | NSM + Founders + Dev | Dev aligned, Sprint 1 unblocked | ⬜ TODO | HIGH
M1 | W2 | Dream Account ABM Plan | Assign 50 dream accounts across BDMs: • Tier 1 (≤10): Personal Founder outreach • Tier 2 (≤20): NSM-led with BDM support • Tier 3 (≤20): BDM-owned Define touchpoint sequence per tier | HubSpot + Excel | NSM + Founders | ABM assignments confirmed, sequences live | ⬜ TODO | HIGH
M1 | W3 | Sales Collateral Audit | Review all existing brochures + presentations Identify gaps: sector-specific collateral needed Commission: 2 new sector decks (Power, Smart City) Upload all to SharePoint /Brochures | SharePoint + Canva | NSM + Founders | SharePoint content hub fully stocked | ⬜ TODO | MED
M1 | W3 | Pipeline Review #1 | First weekly pipeline review with full team: • Review BDM activity vs daily targets • Identify early pipeline formation • Assign 'must-win' accounts | MS Teams + HubSpot | NSM | Pipeline review habit established | ⬜ TODO | HIGH
M1 | W4 | Partner Program Launch | Draft and circulate partner onboarding letter Conduct 2 partner intro calls (Teams) Onboard first 2 partners into HubSpot | Word + Teams + HubSpot | NSM | 2 partners in pipeline | ⬜ TODO | MED
M2 | W5 | Proposal Quality Control | Review every proposal before submission: • Technical accuracy check • Commercial terms aligned with margin targets • Professional formatting (Unicircuit template) • Approve via SharePoint version control | SharePoint + Word | NSM | Zero proposals sent without NSM sign-off | ⬜ TODO | HIGH
M2 | W5 | Tier-1 Account Direct Engagement | NSM personally engages 10 Tier-1 accounts: • Direct call from NSM to CXO / GM level • LinkedIn connect + message • Invite to exclusive webinar/product demo | PBX + LinkedIn + Teams | NSM | 10 Tier-1 accounts contacted at C-level | ⬜ TODO | HIGH
M2 | W6 | Pipeline Velocity Analysis | Analyse HubSpot pipeline: • Days stuck per stage by account • BDM activity-to-pipeline correlation • Identify best-performing BDM behaviors • Share learnings in team meeting | HubSpot + Excel | NSM | Velocity report → team briefing done | ⬜ TODO | HIGH
M2 | W6 | Govt Sales Activation | Lead Govt/PSU workstream: • GeM registration confirmed • Tender response SOP created • CII/FICCI membership initiated • Attend 1 industry event/vendor meet | GeM Portal + Outlook | NSM + Govt Lead | GeM live, 2 tenders tracked | ⬜ TODO | HIGH
M2 | W7 | Team Performance Review | Mid-period (Month 2) BDM performance review: • KPIs: calls, meetings, pipeline ₹ vs target • Identify support needed • Coaching session for underperforming BDM • Recognize top performer | Excel + Teams | NSM → Founders | Formal review done, action plan per BDM | ⬜ TODO | MED
M2 | W8 | LLM Dashboard Review | Review UniIntelligence Dashboard (Sprint 5): • Hot leads — are BDMs actioning? • AI digest — is team using it? • Gaps in CRM logging identified • Feedback to dev team | UniIntelligence Dashboard | NSM | Dashboard adopted, gaps reported to dev | ⬜ TODO | MED
M3 | W9 | Deal Acceleration | Active management of top 5 deals: • Personal involvement in negotiations • Founder loop-in for strategic deals • Accelerate commercial finalization • Weekly WhatsApp update from decision-maker | WA + PBX + Outlook | NSM + Founders | 5 deals in active negotiation | ⬜ TODO | HIGH
M3 | W10 | Win-Loss Analysis | Document all closed/lost deals: • Lost reason categorization • Competitor intel gathered • Win pattern identified (sector/service/price point) • Share with team as learning doc | HubSpot + Excel | NSM | Win/loss report in SharePoint | ⬜ TODO | MED
M3 | W11 | Q2 Hiring Plan | Based on Month 3 pipeline: • Identify new territory (Delhi NCR / Pune / Hyderabad?) • Create JD for next 2 BDMs • Budget approval from Founders | Word + Email | NSM → Founders | Q2 hiring plan approved | ⬜ TODO | HIGH
M3 | W12 | Monthly Business Review (MBR) | Prepare and present Month 3 MBR: • Pipeline: ₹ value by stage + territory • Activities: calls, emails, demos, proposals • Wins, losses, learnings • Q2 forecast + revised 12-month plan | Power BI + Teams | NSM | MBR presented, Q2 plan signed off | ⬜ TODO | HIGH

## 🎖 Dream Accounts
50 DREAM ACCOUNT TRACKER — ABM PROGRAM ¦ Unicircuit Engineering Services
ABM Program: Tier 1 (Founder-Led) = Top 10 ¦ Tier 2 (NSM-Led) = Next 20 ¦ Tier 3 (BDM-Owned) = Final 20 ¦ Update Status weekly in pipeline review
# | Account Name | Sector | Territory | Key Contact | Designation | Tier | Service Line | Potential ₹ | Current Stage | Last Activity | Next Action | BDM Owner | Status
1 | NTPC Koradi | Govt/PSU – Power | Nagpur | GM (O&M) | General Manager | T1 | Industrial Asset Mgmt + Surveillance | ₹4 Cr | Target | – | Cold call + LinkedIn outreach | BDM Nagpur | ⬜ TODO
2 | NTPC Khaperkheda | Govt/PSU – Power | Nagpur | DGM (Electrical) | Deputy GM | T1 | Smart Building + Security | ₹3 Cr | Target | – | Email + WA intro with power sector case study | BDM Nagpur | ⬜ TODO
3 | BHILAI STEEL (SAIL) | Govt/PSU – Steel | Raipur | GM (Civil/Infra) | General Manager | T1 | Physical Security + ELV | ₹3 Cr | Target | – | Cold outreach + industry event connect | BDM Raipur | ⬜ TODO
4 | MSEDCL HQ | Govt/PSU – Power | Nagpur | CGM (IT) | Chief GM | T1 | Digital Infrastructure + Smart Metering | ₹3 Cr | Target | – | Formal letter + email + LinkedIn | NSM | ⬜ TODO
5 | Western Coalfields Ltd | Govt/PSU – Mining | Nagpur | Director (Technical) | Director | T1 | Industrial Asset Mgmt + Surveillance | ₹3.5 Cr | Target | – | Senior management intro via industry body | Founder | ⬜ TODO
6 | Nagpur Smart City Dev Corp | Smart City | Nagpur | CEO / Project Director | C-Suite | T1 | Smart Building + Connectivity | ₹2.5 Cr | Target | – | Formal presentation request + RFP tracking | NSM | ⬜ TODO
7 | MIHAN SEZ (MAHAGENCO) | Industrial/SEZ | Nagpur | GM (Infrastructure) | General Manager | T1 | ELV + Digital Infra + Security | ₹2 Cr | Target | – | Direct meeting request via email | BDM Nagpur | ⬜ TODO
8 | CSIDC Raipur | Govt/PSU | Raipur | Managing Director | MD | T1 | Smart Building + Connectivity | ₹2 Cr | Target | – | Formal letter from Unicircuit + GeM connect | BDM Raipur | ⬜ TODO
9 | AIIMS Raipur | Govt/PSU – Health | Raipur | Superintendent | Hospital Superintendent | T1 | Hospital Surveillance + Access Control | ₹1.5 Cr | Target | – | Email to purchase dept + admin | BDM Raipur | ⬜ TODO
10 | AIIMS Nagpur | Govt/PSU – Health | Nagpur | CMO / Purchase | Chief Medical Officer | T1 | Hospital Security + Smart Building | ₹1.5 Cr | Target | – | Email + WA to admin dept | BDM Nagpur | ⬜ TODO
11 | NIT Raipur | Education | Raipur | Registrar / Purchase Officer | Purchase Officer | T2 | Smart Campus + Surveillance | ₹1 Cr | Target | – | Email to purchase dept | BDM Raipur | ⬜ TODO
12 | VNIT Nagpur | Education | Nagpur | Registrar | Registrar | T2 | Smart Campus + Digital Infra | ₹1 Cr | Target | – | LinkedIn + formal email | BDM Nagpur | ⬜ TODO
13 | Nagpur Metro Rail | Govt/PSU – Transit | Nagpur | GM (IT/Infra) | General Manager | T2 | Physical Security + ELV + CCTV | ₹1.5 Cr | Target | – | Email + CPP portal registration | BDM Nagpur | ⬜ TODO
14 | CSPDCL Raipur | Govt/PSU – Power | Raipur | CGM (IT) | Chief GM | T2 | Digital Infrastructure + Smart Monitoring | ₹1.5 Cr | Target | – | Cold call to CGM office | BDM Raipur | ⬜ TODO
15 | CPWD Raipur | Govt – Construction | Raipur | EE / SE | Executive Engineer | T2 | Smart Building + ELV systems | ₹1 Cr | Target | – | GeM + tender tracking | BDM Raipur | ⬜ TODO
16 | CPWD Nagpur | Govt – Construction | Nagpur | Executive Engineer | EE | T2 | Smart Building + Security | ₹1 Cr | Target | – | GeM + CPP portal | BDM Nagpur | ⬜ TODO
17 | Butibori MIDC Industries | Industrial | Nagpur | Facility Managers | Facility Manager | T2 | Smart Building + Fire Safety | ₹80 L | Target | – | Industrial estate visit | BDM Nagpur | ⬜ TODO
18 | Raipur Smart City | Smart City | Raipur | CEO / PMC | Smart City CEO | T2 | Surveillance + Smart Infra | ₹1.5 Cr | Target | – | Formal presentation request | BDM Raipur | ⬜ TODO
19 | Coal India Limited (Regional) | Govt/PSU – Mining | Nagpur | GM (Civil) | General Manager | T2 | Industrial Surveillance + Safety | ₹2 Cr | Target | – | Industry body introduction | NSM | ⬜ TODO
20 | NBCC Nagpur Projects | Govt – Real Estate | Nagpur | Project Manager | PM | T2 | Smart Building + ELV | ₹1 Cr | Target | – | GeM + tender portal | BDM Nagpur | ⬜ TODO
21 | NBCC Raipur Projects | Govt – Real Estate | Raipur | Project Manager | PM | T2 | Smart Building + ELV | ₹1 Cr | Target | – | GeM + tender portal | BDM Raipur | ⬜ TODO
22 | Raipur Airport (AAI) | Govt – Aviation | Raipur | Airport Director | Airport Director | T2 | Physical Security + CCTV + Access | ₹1.5 Cr | Target | – | LinkedIn + formal letter to AAI HQ | NSM | ⬜ TODO
23 | Nagpur Airport (MIHAN) | Govt – Aviation | Nagpur | Director Operations | Director | T2 | Smart Building + Security | ₹1.5 Cr | Target | – | Email to MIAL procurement | BDM Nagpur | ⬜ TODO
24 | BHEL Raipur | Govt/PSU – Engineering | Raipur | GM (Projects) | General Manager | T2 | Industrial Automation + Security | ₹1 Cr | Target | – | Direct approach via BHEL vendor portal | BDM Raipur | ⬜ TODO
25 | HAL Nagpur Division | Govt/PSU – Defence | Nagpur | GM (Infrastructure) | General Manager | T2 | Smart Building + Access Control | ₹1 Cr | Target | – | Formal letter + empanelment | NSM | ⬜ TODO
26 | NMC (Nagpur Municipal) | Govt – Urban | Nagpur | Commissioner / DCP | Municipal Commissioner | T2 | Smart City + Surveillance | ₹1.5 Cr | Target | – | Smart City initiative outreach | BDM Nagpur | ⬜ TODO
27 | Raipur Municipal Corporation | Govt – Urban | Raipur | Commissioner | Municipal Commissioner | T2 | Smart City + Surveillance | ₹1 Cr | Target | – | Smart City initiative outreach | BDM Raipur | ⬜ TODO
28 | Ultratech Cement (Chhattisgarh) | Industrial | Raipur | Head – Projects | Project Head | T2 | Industrial Asset Mgmt | ₹80 L | Target | – | Industry event + email | BDM Raipur | ⬜ TODO
29 | NSEZ Raipur | Industrial/SEZ | Raipur | CEO / Project Director | CEO | T2 | Connectivity + Smart Building | ₹1 Cr | Target | – | Direct approach to NSEZ office | BDM Raipur | ⬜ TODO
30 | BEL Nagpur | Govt/PSU – Defence | Nagpur | GM (Purchase) | General Manager | T2 | Smart Building + Surveillance | ₹80 L | Target | – | Vendor registration + direct contact | NSM | ⬜ TODO
31 | Finolex Industries Nagpur | Industrial | Nagpur | Plant Head | Plant Head | T3 | Industrial Asset Mgmt | ₹50 L | Target | – | Cold email + LinkedIn | BDM Nagpur | ⬜ TODO
32 | Reliance Retail (CG warehouse) | Commercial | Raipur | Facility Manager | Facility Mgr | T3 | Smart Building + Security | ₹40 L | Target | – | Email + WA | BDM Raipur | ⬜ TODO
33 | Amazon Fulfillment (Nagpur) | Commercial | Nagpur | Operations Manager | Ops Manager | T3 | Physical Security + Connectivity | ₹40 L | Target | – | Cold email + LinkedIn | BDM Nagpur | ⬜ TODO
34 | Flipkart Warehouse (Nagpur) | Commercial | Nagpur | Facility Head | Facility Head | T3 | Smart Surveillance + ELV | ₹40 L | Target | – | Email + WA | BDM Nagpur | ⬜ TODO
35 | Tata Power (CG distribution) | Industrial/Power | Raipur | Circle Manager | Circle Manager | T3 | Smart Monitoring + Digital Infra | ₹60 L | Target | – | Cold call + email | BDM Raipur | ⬜ TODO
36 | JSW Energy (CG) | Industrial/Power | Raipur | Head – O&M | Head O&M | T3 | Industrial Surveillance + Safety | ₹60 L | Target | – | Email + industry intro | BDM Raipur | ⬜ TODO
37 | MAHAGENCO Koradi | Govt/PSU – Power | Nagpur | GM (Civil) | General Manager | T3 | Smart Building + Security | ₹60 L | Target | – | Call + email to GM office | BDM Nagpur | ⬜ TODO
38 | NIT Nagpur (VNIT allied) | Education | Nagpur | Purchase Officer | Purchase Officer | T3 | Smart Campus | ₹40 L | Target | – | Email to purchase dept | BDM Nagpur | ⬜ TODO
39 | Central Railway (Nagpur HQ) | Govt/PSU – Railways | Nagpur | DRM / Sr.DEE | Divisional Rail Mgr | T3 | CCTV + Access + ELV | ₹80 L | Target | – | Formal request + empanelment | NSM | ⬜ TODO
40 | South East Central Railway | Govt/PSU – Railways | Raipur | DRM | Divisional Rail Mgr | T3 | CCTV + Access + ELV | ₹80 L | Target | – | Tender + empanelment approach | BDM Raipur | ⬜ TODO
41 | Raipur Airport Hotels (ITDC) | Commercial | Raipur | GM | General Manager | T3 | Smart Building + Security | ₹30 L | Target | – | Direct visit + email | BDM Raipur | ⬜ TODO
42 | PNB / SBI Regional Offices | Commercial – Banking | Nagpur + Raipur | Facilities Manager | Facility Manager | T3 | Physical Security + ELV | ₹30 L | Target | – | Email to regional FM | Both BDMs | ⬜ TODO
43 | Nagpur University Campus | Education | Nagpur | Registrar | Registrar | T3 | Smart Campus + Surveillance | ₹30 L | Target | – | Email + campus visit | BDM Nagpur | ⬜ TODO
44 | PT Usha Institute CG | Education | Raipur | Director | Director | T3 | Smart Building + Security | ₹20 L | Target | – | Direct call + email | BDM Raipur | ⬜ TODO
45 | Dainik Bhaskar HQ (Raipur) | Commercial – Media | Raipur | Facility Manager | FM | T3 | Smart Building + Access | ₹20 L | Target | – | Direct visit | BDM Raipur | ⬜ TODO
46 | Mahindra Logistics Park (Nagpur) | Commercial – Logistics | Nagpur | Operations Head | Ops Head | T3 | Surveillance + Connectivity | ₹40 L | Target | – | Email + LinkedIn | BDM Nagpur | ⬜ TODO
47 | Wardha Pharma Cluster | Industrial | Nagpur | Cluster Chairman | Chairman | T3 | Industrial Asset Mgmt | ₹30 L | Target | – | CII introduction | BDM Nagpur | ⬜ TODO
48 | MHADA Colony Nagpur | Govt – Housing | Nagpur | Executive Engineer | EE | T3 | Smart Building + ELV | ₹30 L | Target | – | GeM + direct call | BDM Nagpur | ⬜ TODO
49 | AIIMS Bhopal (National) | Govt/PSU – Health | National | Purchase Officer | Purchase Officer | T3 | Hospital Security + Smart Building | ₹50 L | Target | – | GeM + tender portal | NSM | ⬜ TODO
50 | NTPC Sipat (CG) | Govt/PSU – Power | Raipur | GM (O&M) | General Manager | T3 | Industrial Asset Mgmt | ₹2 Cr | Target | – | Email + industry network | BDM Raipur | ⬜ TODO

## 📊 Pipeline Review
WEEKLY PIPELINE REVIEW TEMPLATE — MONDAY STANDUP ¦ Unicircuit Sales Team
Fill before every Monday 9 AM pipeline review ¦ Owner: Each BDM fills their section ¦ NSM reviews totals ¦ Founders review Tier-1 deals only
SECTION A: PIPELINE SUMMARY (All Territories Combined)
Stage | Raipur Deals | Raipur ₹ | Nagpur Deals | Nagpur ₹ | National Deals | National ₹ | TOTAL Deals | TOTAL ₹ | vs Last Week | Trend
Target (Not Contacted) | – | – | – | – | – | – | – | – | – | –
Contacted (1st Touch) | – | – | – | – | – | – | – | – | – | –
Demo Scheduled | – | – | – | – | – | – | – | – | – | –
Demo Done / Qualified | – | – | – | – | – | – | – | – | – | –
Proposal Submitted | – | – | – | – | – | – | – | – | – | –
Negotiation | – | – | – | – | – | – | – | – | – | –
Won | – | – | – | – | – | – | – | – | – | –
Lost | – | – | – | – | – | – | – | – | – | –
TOTAL ACTIVE PIPELINE | – | – | – | – | – | – | – | – | – | –
SECTION B: TOP 5 HOT DEALS THIS WEEK (Tier 1 + Active Negotiations)
Account | Stage | Value ₹ | Decision Maker | Last Touch | Last Touch Summary | Next Action | By When | BDM
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
SECTION C: BLOCKERS & SUPPORT NEEDED
Deal / Account | BDM | Blocker Description | Support Needed From | By When | Status
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
SECTION D: WINS THIS WEEK (Milestones: Demo Booked / Proposal Sent / PO Received)
Win Type | Account | BDM | Details | Pipeline Impact ₹ | Next Step
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –
– fill in – | – fill in – | – fill in – | – fill in – | – fill in – | – fill in –

## ✉ Message Templates
SALES MESSAGE TEMPLATES — EMAIL + WHATSAPP ¦ Unicircuit Engineering Services
All templates pre-approved. BDMs personalise the [brackets] only. LLM Platform auto-generates context-specific versions based on contact history.
[EMAIL-01] Cold Intro — Govt/PSU — Subject: Smart Building & Security Solutions for [Organization Name]
Dear [Title] [Name], I hope this message finds you well. I am [Your Name] from Unicircuit Engineering Services, a technology firm specializing in Smart Building Ecosystems, Physical Security & Surveillance, and Industrial Asset Management for Government and PSU organizations. We have recently delivered projects for organizations similar to [Organization] in the [Power/Infrastructure/Health] sector, significantly improving [operational efficiency / security posture / asset visibility]. I would appreciate 20 minutes of your time to present how our solutions can benefit [Organization Name]. Would [specific date] at [time] work for a brief Teams call or in-person meeting? I am also sharing our capability overview: [SharePoint link] Warm regards, [Your Name] ¦ [Designation] Unicircuit Engineering Services [Mobile] ¦ [Email]
[EMAIL-02] Follow-Up After No Reply (Day 5) — Subject: Re: Smart Solutions for [Organization] — Following Up
Dear [Name], I hope you had a chance to review my earlier note. I understand priorities are demanding — I wanted to briefly resurface this as I believe our [Smart Surveillance / Smart Building / Asset Management] solutions could directly address challenges being faced at [Organization]. We are currently working with [reference organization type] and have achieved [key outcome, e.g., 40% reduction in security incidents / 30% energy savings]. Would a 15-minute exploratory call this week work? I am happy to work around your schedule. Best regards, [Name] ¦ Unicircuit
[EMAIL-03] Post-Demo Thank You + Proposal Trigger — Subject: Thank You — [Meeting Summary] ¦ Unicircuit Proposal to Follow
Dear [Name], Thank you for the productive discussion today regarding [specific topic discussed]. It was very helpful to understand [Organization]'s requirements around [specific need]. As discussed, I will prepare a detailed proposal covering: • [Service Line 1]: [brief scope] • [Service Line 2]: [brief scope] • Implementation timeline: [X weeks] You can expect the proposal by [specific date]. In the meantime, I am sharing our detailed case study relevant to your use case: [SharePoint link] Please feel free to reach out with any questions. Warm regards, [Name]
[EMAIL-04] Tender / RFQ Acknowledgement — Subject: Re: [Tender Reference No.] — Unicircuit Engineering Services Expression of Interest
Dear [Name / Tender Officer], We acknowledge receipt of [Tender/RFQ Reference: XXXX] for [Brief Description]. Unicircuit Engineering Services is pleased to confirm our interest in participating in this tender. We are a registered vendor on GeM (Seller ID: XXXXXXX) and meet the technical and financial eligibility criteria. We are currently reviewing the tender documents and will submit a comprehensive, compliant response before the due date of [Date]. Should you require any pre-bid clarifications or a technical presentation, we are available at your convenience. Regards, [NSM Name] ¦ Unicircuit Engineering Services [GeM ID] ¦ [Contact]
[WA-01] Cold Intro WhatsApp — WhatsApp Business Message
Hi [Name], I'm [Your Name] from Unicircuit Engineering Services 🏢 We specialize in Smart Building, Physical Security & Surveillance, and Industrial Asset Management for organizations like [their sector]. We recently delivered a [relevant project type] for [reference org type] — happy to share a 2-page brief. Would you be open to a quick 15-min call this week? 📞 [Your Name] ¦ Unicircuit [Mobile number]
[WA-02] Post-Email Follow-Up (WhatsApp) — WhatsApp — 72 hrs after email sent
Hi [Name], hope you're well! I had sent an email earlier regarding Unicircuit's Smart Building & Security solutions for [Organization]. Just wanted to check if you had a chance to look at it. 🙏 Our company deck: [SharePoint link] Happy to arrange a call at your convenience — just reply to this message or call me directly. [Name] ¦ Unicircuit Engineering
[WA-03] Demo Confirmation — WhatsApp — 24 hrs before demo
Hi [Name]! Looking forward to our discussion tomorrow 📅 🗓 Date: [Date] ⏰ Time: [Time] IST 📍 Via: [MS Teams / Office address] Teams link: [link] We'll be covering: [Smart Surveillance / Smart Building / Asset Mgmt] for [Organization]. If you need to reschedule, just let me know. See you tomorrow! 👋 [Name] ¦ Unicircuit
[WA-04] Tender Alert to Partners — WhatsApp Group — Partner Network
🔔 TENDER ALERT — Unicircuit Partner Network Organisation: [NTPC / CPWD / MSEDCL / etc.] Ref No: [Tender Reference] Scope: [Brief description] Est. Value: ₹[X] Cr Submission Deadline: [Date] Unicircuit is responding. If you are interested in co-bidding or subcontracting, reply YES by [date]. Tender doc: [link] [NSM Name] ¦ Unicircuit Engineering Services